## Sheet1
Timeline (updated May 15th 2019)
|  | May |  |  | June |  |  |  | July |  |  |  |  | August |  |  | September |  |  |  | October
| w/c | 13th | 20th | 27th | 3rd | 10th | 17th | 24th | 1st | 8th | 15th | 22nd | 29th | 12th | 19th | 26th | 2nd | 9th | 16th | 23rd | (30th) | 1st | 7th | 14th | 21st | 28th
General | Agree budgets going forward (inc. SEA/HRA) | bar: May 13th
| SG meeting | May 27th: 29th
Design codes | Speak to Aecom regarding Design Codes | bar: May 13th to May 20th
AECOM undertake and finalise design codes | bar: May 13th to May 20th; June 3rd to June 24th
SEA | Agree who is doing the SEA work | bar: May 13th
If AE, prepare SEA Scoping / HRA screening | bar: May 20th to June 3rd
Prepare maps for the SEA work | bar: May 27th to June 3rd
5 week consultation on SEA Scoping Report | bar: June 10th to July 8th
Commence work on full SEA report | bar: June 17th to July 1st; July 15th to July 22nd
Consult for 6 weeks on SEA | bar: July 29th to September 9th
Draft NP | Distribute draft NP for discussion | bar: May 20th
Update Plan based on May SG meeting | bar: June 10th to July 1st
Undertake bulk of NP mapping
Finalise Plan to incorpororate SEA feedback and Design Code work | bar: July 1st to July 8th
Parish Council endorse draft Plan | bar: July 15th; October 21st
Amend Plan in light of Reg. 14 comments | bar: October 7th to October 14th
Submit to HDC | bar: October 28th
Regulation 14 | Prepare publicity and events for Regulation 14 | bar: June 10th to July 29th
Update website with all relevant documents | bar: July 15th to July 29th
Prepare feedback form | bar: July 8th
finalise list of statutory and non-statutory consultees | bar: July 22nd
Hold likely 8 week consultation | bar: July 29th to September 23rd
Hold public events | bar: July 29th; August 19th; September 9th; September 23rd
BSC/ CS | Draft Basic Conditions Statement | bar: September 9th to September 16th
Draft Consultation Statement | bar: September 9th to September 16th
Finalise both statements post consultation | bar: October 7th to October 14th
Prepare schedule of feedback from Reg 14 | bar: October (30th) to October 1st